## Cover sheet
Fostering Recruitment Support Hub Implementation Plan Template
This workbook includes:
1 | Implementation Plan template
This plan can be populated by clusters and submitted to the DfE as part of their response to Question 2 of the Stage 2 bid application. All text in italics are examples and should be replaced with relevant details by clusters. The headings are also only suggestions that could be workstreams for the project, some may be combined or are not relevant so can be removed.
2 | Risk register:
This tab contains headers you may wish to use for your risk register which is also required as part of your response in Question 2. Again these are only suggestions and are not intended to be prescriptive.

## Implementation plan
Implementation Plan - Fostering Recruitment Hub
| Milestones at the top |  | Timetable
# | Activity | Roles and responsibilities | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Co-design and set-up phase
Milestones:
1 | Project Management and oversight
1.1 | Regular check-ins with workstreams | Project manager and workstream leads
1.2 | Monthly boards with senior representatives from LAs | Project manager with senior representation
1.3 | Monthly engagement with Coaches and DfE
1.4 | Cabinet reporting schedule
2 | Legal
2.1 | Develop/ refine existing partnership agreement to ensure fit for purpose e.g. delegated powers, information sharing | Legal Lead
2.2 | All LA legal leads to sign off agreement
2.3 | Sign off at board
3 | Hub design and support offer
3.1 | Workshops to test hub design and support offer | Service Design Lead
3.2 | Detailed design of the hub including staffing structure, leadership and front door
3.3 | Detailed review of current support offer across the LAs to identify areas that can be standardised
4 | Standarising processes
4.1 | Review of processes for preparation, assessment and approval
4.2 | Agree areas for standardisation
5 | Frontdoor
5.1 | Webiste design and procurement | Service Design Lead/ PM
5.2 | Define telephony requirements and procurement
6 | ICT and data
6.1 | Define rquirements for case management system | ICT lead
6.2 | Procure system (if required)
7 | HR
7.1 | Engagement events as required to support staff through change process | HR lead
7.2 | Recruit to fulfill roles in hub
7.3 | Support onboarding of staff into team
8 | Communications
8.1 | Promote within LAs and make aware of change | Communications Lead
9 | Finance
9.1 | Oversee grant process and ongoing returns | Finance Lead
9.2 | Engage with leads from all LA's to consider sustainability
Go live and ongoing operations
10 | Launch recruitment hub
11 | Operations
12 | Finance
13
14
15
16
17
Recruitment hub operational
Communications campaign live

## Risk register
Risk register
# | Date logged | Risk | Description | Owner | Likelihood (1=low; 3=high) | Impact (1=low; 3=high) | Risk Score | Mitigating Actions | Comments / Status
1 | 2023-08-25 | Tight timeframe for delivery | If decisions are not made quickly within the tight timescales of the project, there would be delays to project delivery | Project Sponsor (Lead DCS) | 2 | 3 | 6 | Clear implementation plan with regular reviews and risk monitoring by the Project Board.
2 | 2023-08-25 | Disagreement about the remit of the hub | If there is disgreement amongst local authorities in the cluster on the remit and functions of the recruitment support hub it could cause delays to project delivery | Project Sponsor (Lead DCS) | 2 | 3 | 6 | Each local authority should identify a lead to engage with design of the hubs remit and processes and ensure strong awareness of the remote of the recruitment support hub and its impact on existing local authority fostering services to minimise a lack of understanding in individual local authorities.
3 | 2023-08-25 | Change in leadership | If leadership, such as the Director of Children's Services changes in a local authority, new leaders may lack understanding of the project or its ambition and buy-in to the project could be lost | Project Sponsor (Lead DCS) | 2 | 2 | 4 | Each local authorities lead engaging with the Project Board should ensure strong awareness of the remit of the recruitment support hub and impact on existing local authority fostering services to avoid disagreement. The Project Sponsor to quickly build relationships with new leaders.
4 | 2023-08-25 | Unable to agree contents of collaboration agreement within proposed timescales | If partners are not able to agree on the contents of a partnership agreement within the agreed timescales, this could stop the recruitment support hub going live. | Project Sponsor (Lead DCS) | 1 | 3 | 3 | Ensure there is a strong leadership commitment to participate in coorproduction for project activities such as a the partnership agreement, within clear timescales.
| 2023-08-25 | Process to sign-off collaboration agreement take longer than expected | Bureaucratic processes required in local authorities to obtain signatures on the agreed document take longer than initially projected by individual local authorities. | Individual local authority representatives at Project Board | 2 | 3 | 6 | Each local authority should be required to provide clear written requirements and timescales for their internal processes to obtain signatures
5 | 2023-08-25 | Local authority wants to leave cluster | A local authority could wish to leave the cluster during implementation having an impact on the funding from DfE and overall programme aims | Project Sponsor (Lead DCS) | 2 | 3 | 6 | Clear stakeholder understanding of the project benefits at all levels of each organisation from the outset of the project. Strong relationships maintained at leadership level by the Project Sponsor.
6 | 2023-08-25 | Local authority wants to join cluster | A local authority could wish to join the cluster during the implementation or go live phase which could impact the scope of the project and suitability of the funding profile. | Project Sponsor (Lead DCS) | 1 | 3 | 3 | Clear stakeholder understanding of the project scope and possibility to be involved at certain stages of the project, such as following the DfE funding ending. Strong engagement at the leadership level on possibility to engage in the long-term.
7 | 2023-08-25 | Local authority has Ofsted inspection | A local authority may have an Ofsted inspection during the project lifecycle which impacts their ability to engage with the project due to limited resource. | Individual local authority representatives at Project Board, Project Sponsor (Lead DCS) | 3 | 3 | 9 | Each local authorities lead engaging with the Project Manager where capacity may be limited or they cannot attend meetings and workshops. Clear updates about progress at the Project Board and engagement by local authority representatives to ensure awareness of progress made.
8 | 2023-08-25 | Local authorities lack capacity to engage with project | Local authorities may lack the capacity to engage with the project due to sickness, gholiday or other work commitments which could impact buy-in or their ability to engage with delivery and meet timescales. | Individual local authority representatives at Project Board, Project Sponsor (Lead DCS) | 3 | 3 | 9 | Each local authorities lead engaging with the Project Manager where capacity may be limited or they cannot attend meetings and workshops. Clear updates about progress at the Project Board and engagement by local authority representatives to ensure awareness of progress made.