## Cover sheet
Fostering Recruitment Support Hub Implementation Plan Template
This workbook includes:
1 | Implementation Plan template
This plan can be populated by clusters and submitted to the DfE as part of their response to Question 2 of the Stage 2 bid application. All text in italics are examples and should be replaced with relevant details by clusters. The headings are also only suggestions that could be workstreams for the project, some may be combined or are not relevant so can be removed.
2 | Risk register:
This tab contains headers you may wish to use for your risk register which is also required as part of your response in Question 2. Again these are only suggestions and are not intended to be prescriptive.

## Implementation plan
Implementation Plan - Fostering Recruitment Hub
| Milestones at the top |  | Timetable
# | Activity | Roles and responsibilities | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Co-design and set-up phase
Milestones:
1 | Project Management and oversight
1.1 | Regular check-ins with workstreams | Project manager and workstream leads
1.2 | Monthly boards with senior representatives from LAs | Project manager with senior representation
1.3 | Monthly engagement with Coaches and DfE
1.4 | Cabinet reporting schedule
2 | Legal
2.1 | Develop/ refine existing partnership agreement to ensure fit for purpose e.g. delegated powers, information sharing | Legal Lead
2.2 | All LA legal leads to sign off agreement
2.3 | Sign off at board
3 | Hub design and support offer
3.1 | Workshops to test hub design and support offer | Service Design Lead
3.2 | Detailed design of the hub including staffing structure, leadership and front door
3.3 | Detailed review of current support offer across the LAs to identify areas that can be standardised
4 | Standarising processes
4.1 | Review of processes for preparation, assessment and approval
4.2 | Agree areas for standardisation
5 | Frontdoor
5.1 | Webiste design and procurement | Service Design Lead/ PM
5.2 | Define telephony requirements and procurement
6 | ICT and data
6.1 | Define rquirements for case management system | ICT lead
6.2 | Procure system (if required)
7 | HR
7.1 | Engagement events as required to support staff through change process | HR lead
7.2 | Recruit to fulfill roles in hub
7.3 | Support onboarding of staff into team
8 | Communications
8.1 | Promote within LAs and make aware of change | Communications Lead
9 | Finance
9.1 | Oversee grant process and ongoing returns | Finance Lead
9.2 | Engage with leads from all LA's to consider sustainability
Go live and ongoing operations
10 | Launch recruitment hub
11 | Operations
12 | Finance
13
14
15
16
17
Recruitment hub operational
Communications campaign live

## Risk register
Risk register
# | Date logged | Description | Impact | Owner | Likelihood (1=low; 3=high) | Impact (1=low; 3=high) | Risk Score | Mitigating Actions | Comments / Status
1 | 2023-09-01 | Risk 1